## COST ESTIMATE
Project Cost Estimation				Resource	Task	S0	S1	S2	S3	S4	S5	S6	S7	€/h	Hours	TOTAL €

Work Category	Price €/h				Team Leader/ Generalist
Project management	80,00 €			Joni	Project management	3	10	8	15	15	15	10	10	80,00 €	86	6 880,00 €		Total Working Hours	2235 h
Server maintanance/administration	60,00 €				Server maintanance/administration	0	0	1	2	2	2	1	1	60,00 €	9	540,00 €		TOTAL WORK COST	136 210,00 €
Familiarization	45,00 €				Familiarization	20	12	10	2	2	2	2	2	45,00 €	52	2 340,00 €		Work cost with Profit 15 %	156 641,50 €
Planning/Design	60,00 €				Planning	0	4	4	8	8	6	2	2	60,00 €	34	2 040,00 €		Work cost with profit & VAT 25,5%	196 585,08 €
Implementation	70,00 €				Implementation	0	0	6	6	6	6	4	0	70,00 €	28	1 960,00 €
Documentation	60,00 €				Documentation	1	8	5	8	8	8	15	15	60,00 €	68	4 080,00 €
Testing	70,00 €				Testing	0	0	0	0	0	0	0	0	70,00 €	0	0,00 €
Meetings	55,00 €				Meetings	5	10	8	10	10	10	10	5	55,00 €	68	3 740,00 €		Task	Total hours in category
Other	90,00 €				Other	1	1	1	1	1	1	1	1	90,00 €	8	720,00 €		Project management	145
					TOTAL Hours	30	45	43	52	52	50	45	36		353			Server maintanance/administration	125
															Total Cost:	22 300,00 €		Familiarization	400
					Software Testing 1													Planning	226
				Juha	Project management	1	1	1	1	1	1	1	1	80,00 €	8	640,00 €		Implementation	308
Total cost per work category					Server maintanance/administration	0	0	1	1	1	1	1	1	60,00 €	6	360,00 €		Documentation	336
					Familiarization	20	15	10	8	2	2	2	2	45,00 €	61	2 745,00 €		Testing	222
Work Category	Cost Estimate				Planning	0	4	4	8	8	8	2	2	60,00 €	36	2 160,00 €		Meetings	408
Project management	11 600,00 €				Implementation	0	0	0	0	0	0	0	0	70,00 €	0	0,00 €		Other	65
Server administration	7 500,00 €				Documentation	1	10	6	6	6	6	20	10	60,00 €	65	3 900,00 €
Familiarization	18 000,00 €				Testing	0	0	10	16	20	20	25	10	70,00 €	101	7 070,00 €
Planning	13 560,00 €				Meetings	5	10	8	10	10	10	10	5	55,00 €	68	3 740,00 €		Division of Labour
Implementation	21 560,00 €				Other	1	1	1	1	1	1	1	1	90,00 €	8	720,00 €
Documentation	20 160,00 €				TOTAL Hours	28	41	41	51	49	49	62	32		353
Testing	15 540,00 €														Total Cost:	21 335,00 €
Meetings	22 440,00 €				Software Testing 2
Other	5 850,00 €			Teemu	Project management	1	1	2	3	3	3	3	2	80,00 €	18	1 440,00 €
					Server maintanance/administration	0	0	0	0	0	0	0	0	60,00 €	0	0,00 €
					Familiarization	30	40	17	10	2	2	2	2	45,00 €	105	4 725,00 €
					Planning	0	5	8	15	15	15	8	1	60,00 €	67	4 020,00 €
					Implementation	0	0	0	0	0	0	0	0	70,00 €	0	0,00 €
					Documentation	0	3	4	8	8	8	15	8	60,00 €	54	3 240,00 €
					Testing	0	0	1	16	20	20	25	19	70,00 €	101	7 070,00 €
					Meetings	5	10	8	10	10	10	10	5	55,00 €	68	3 740,00 €
					Other	1	1	1	1	1	1	1	1	90,00 €	8	720,00 €
					TOTAL Hours	37	60	41	63	59	59	64	38		421
															Total Cost:	24 955,00 €
					Security
				Jarmo	Project management	0	0	0	0	0	0	0	0	80,00 €	0	0,00 €
					Server maintanance/administration	0	0	1	1	1	1	1	3	60,00 €	8	480,00 €
					Familiarization	25	10	10	8	8	8	0	0	45,00 €	69	3 105,00 €
					Planning	0	4	4	6	6	6	2	2	60,00 €	30	1 800,00 €
					Implementation	0	0	9	20	20	20	6	5	70,00 €	80	5 600,00 €
					Documentation	4	10	5	5	5	5	15	14	60,00 €	63	3 780,00 €
					Testing	0	0	0	0	0	0	0	0	70,00 €	0	0,00 €
					Meetings	5	10	8	10	10	10	10	5	55,00 €	68	3 740,00 €
					Other	1	1	1	1	1	1	1	1	90,00 €	8	720,00 €
					TOTAL Hours	35	35	38	51	51	51	35	30		326
															Total Cost:	19 225,00 €
					Operations/Adminstrator
				Mikko	Project management	0	2	2	2	2	2	2	2	80,00 €	14	1 120,00 €
					Server maintanance/administration	0	2	15	15	15	15	15	15	60,00 €	92	5 520,00 €
					Familiarization	12	15	3	3	3	3	3	3	45,00 €	45	2 025,00 €
					Planning	2	5	5	5	5	5	5	5	60,00 €	37	2 220,00 €
					Implementation	22	20	8	8	8	8	8	8	70,00 €	90	6 300,00 €
					Documentation	2	2	4	4	4	4	4	4	60,00 €	28	1 680,00 €
					Testing	0	2	3	3	3	3	3	3	70,00 €	20	1 400,00 €
					Meetings	5	10	8	10	10	10	10	5	55,00 €	68	3 740,00 €
					Other	2	2	3	3	3	3	3	3	90,00 €	22	1 980,00 €
					TOTAL Hours	45	60	51	53	53	53	53	48		416
															Total Cost:	25 985,00 €
					Developer
				Tugba	Project management	1	3	2	2	3	3	3	2	80,00 €	19	1 520,00 €
					Server maintanance/administration	0	1	1	2	2	2	1	1	60,00 €	10	600,00 €
					Familiarization	20	15	15	4	4	4	4	2	45,00 €	68	3 060,00 €
					Planning	0	4	4	6	2	2	2	2	60,00 €	22	1 320,00 €
					Implementation	0	10	10	20	20	20	20	10	70,00 €	110	7 700,00 €
					Documentation	1	8	5	4	5	5	15	15	60,00 €	58	3 480,00 €
					Testing	0	0	0	0	0	0	0	0	70,00 €	0	0,00 €
					Meetings	5	10	8	10	10	10	10	5	55,00 €	68	3 740,00 €
					Other	1	1	1	2	2	2	1	1	90,00 €	11	990,00 €
					TOTAL Hours	28	52	46	50	48	48	56	38		366
															Total Cost:	22 410,00 €

## FEATURE PRICES
	FEATURE PRICING

EPIC	Feature Description	In Plan	Priority*	Familiarization	Design	Implementation	Testing	Documentation	Deployment	Total Hours	Total Work Price	With 15 % Profit	+ With 25,5% VAT
			Price per Hour:	45,00 €	60,00 €	70,00 €	70,00 €	60,00 €	60,00 €
EPIC02: Service deployment	FEA005: Automate build,test, and deployment processes	X	A	2	2	10	8	4	8	34	2 190,00 €	2 518,50 €	3 160,72 €
	FEA004: Implement CI/CD pipelines for all services	X	B	2	3	9	5	2	12	33	2 090,00 €	2 403,50 €	3 016,39 €
EPIC03: Prestashop as service	FEA006 Provide managed hosting for PrestaShop instances	X	A	6	6	14	4	2	6	38	2 370,00 €	2 725,50 €	3 420,50 €
	FEA007 Dockerized Service Production	X	A	4	2	8	5	2	12	33	2 050,00 €	2 357,50 €	2 958,66 €
	FEA008 Secure Service Access	X	A	4	3	10	6	2	4	29	1 840,00 €	2 116,00 €	2 655,58 €
	FEA078 Server management	X	A	16	2	10	4	4	20	56	3 260,00 €	3 749,00 €	4 704,99 €
	FEA009 Provide API access for developers to integrate with other services	X	B	10	3	14	6	4	6	43	2 630,00 €	3 024,50 €	3 795,75 €
EPIC04: Log management	FEA010 Provide real-time log monitoring and analysis capabilities	X	A	6	3	12	6	2	6	35	2 190,00 €	2 518,50 €	3 160,72 €
EPIC05: Security Enhancements	FEA017 Implement security contexts (e.g., run as non-root user) to enhance container security	X	A	8	2	8	8	4	4	34	2 080,00 €	2 392,00 €	3 001,96 €
	FEA015 Implement PrestaScan Security to scan PrestaShop website	X	B	10	2	12	14	4	2	44	2 750,00 €	3 162,50 €	3 968,94 €
	FEA016 Set up the security modules	X	B	12	2	12	12	8	6	52	3 180,00 €	3 657,00 €	4 589,53 €
	FEA020 Database security hardening	X	C	16	3	12	16	6	2	55	3 340,00 €	3 841,00 €	4 820,45 €
EPIC06: Test Automation	FEA022 Acceptance Test Automation	X	A	10	3	8	18	2	1	42	2 630,00 €	3 024,50 €	3 795,75 €
	FEA023 Integrate test automation into the CI/CD pipeline	X	A	10	3	10	10	2	2	37	2 270,00 €	2 610,50 €	3 276,18 €
EPIC07: Bug fixes	FEA028 Ensure efficient bug reporting and triage processes	X	A	8	2	8	6	8	1	33	2 000,00 €	2 300,00 €	2 886,50 €
	FEA029 Utilize error tracking tools to proactively identify and address issues	X	A	12	2	12	8	4	1	39	2 360,00 €	2 714,00 €	3 406,07 €
	FEA030 Integrate with version control systems (e.g., Git)	X	A	4	2	6	6	2	1	21	1 320,00 €	1 518,00 €	1 905,09 €
	FEA031 Assign bugs to developers and track progress towards resolution	X	A	4	2	8	4	6	1	25	1 560,00 €	1 794,00 €	2 251,47 €
EPIC08: Registration and login	FEA035 Secure user login	X	A	4	2	8	12	2	1	29	1 880,00 €	2 162,00 €	2 713,31 €
	FEA036 Password recovery	X	A	4	2	8	10	2	1	27	1 740,00 €	2 001,00 €	2 511,25 €
Epic09: Service Backup	FEA039 Automated Database Backup. Implement automated scheduling for regular database backups	X	B	8	3	16	8	2	2	39	2 460,00 €	2 829,00 €	3 550,39 €
	FEA040 Implement automated backups of the entire PrestaShop installation, including files, images, and themes	X	B	4	3	16	8	2	2	35	2 280,00 €	2 622,00 €	3 290,61 €
EPIC10: Performance Tuning	FEA045 Page Caching: Implement efficient page caching mechanisms	X	B	8	3	10	4	2	2	29	1 760,00 €	2 024,00 €	2 540,12 €
EPIC12: Customer Feedback	FEA052 General Feedback Forms	X	C	1	4	6	2	1	1	15	965,00 €	1 109,75 €	1 392,74 €
EPIC15:Documentation and training	FEA062 General documentation	X	A	1	2	2	1	20	1	27	1 635,00 €	1 880,25 €	2 359,71 €
	FEA071 Implement and maintain data privacy policies and procedures in compliance with relevant regulations	X	A	2	2	8	2	10	1	25	1 570,00 €	1 805,50 €	2 265,90 €
	FEA073 Clear crisis communication guidelines and practices	X	B	2	2	3	1	10	1	19	1 150,00 €	1 322,50 €	1 659,74 €
	FEA074 A Risk Management Checklist for Prestashop	X	B	4	2	4	1	8	1	20	1 190,00 €	1 368,50 €	1 717,47 €
			Total Price	8 190,00 €	4 320,00 €	18 480,00 €	13 650,00 €	7 620,00 €	6 480,00 €	598	59 338,00 €	68 238,70 €	85 298,38 €

*Priority levels explained: / A = Must have / B = Important / C = Nice to have